ANNEX 8:

ESTIMATED TIME FRAME FOR PROCESSING GRANT APPLICATIONS

| TIME FRAME | ACTIVITIES | MAIN ACTORS |
| --- | --- | --- |
| 1 week | Preparation for PCN Call | NARDF Secretariat |
| 5 weeks | Development of PCN and Submission to NARDF | GOs, NGOs, CBOs, Research Institutions, Teaching Institutions |
| 5 weeks | Pre-screening of PCN and allocation to peer reviewers for evaluation | NARDF Secretariat |
| 2 weeks | Evaluation of PCN | Peer Reviewers |
| 2 week | Compilation of evaluation results and discussions | NARDF Secretariat, TSC |
| 1 week | Approval of PCN and notification | FMC |
| 1 week | Preparation For FPP Call | NARDF Secretariat |
| 5 weeks | Development of FPP and submission to NARDF | GOs, NGOs, CBOs, Research Institutions, Teaching Institutions |
| 2 weeks | Prescreening of FPP and allocation to peer reviewers for evaluation | NARDF Secretariat |
| 2 weeks | Evaluation of FPP | Peer Reviewers |
| 3 weeks | Compilation of evaluation results and discussions | NARDF Secretariat, TSC |
| 1 week | Approval of FPP and notification | FMC |
| 4 weeks | Negotiations | TSC/NARDF Officer |
| 2 week | Contract Agreement | NARDF |

Total 36 weeks